## Color
PROJECT: WiFi Bulb Music Sync
Ryan Urquhart |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Holiday
WiFi Bulb Music Sync
Project start date: | 2024-10-01 |  |  |  | October | [34 empty] | November
Scrolling increment: | 0 | time axis 2024-10-01 to 2024-11-25
Milestone description | Category | Progress | Start | Days | time axis 2024-10-01 to 2024-11-25
Project Research
Develop Project Specification | On Track | 100% | 2024-10-01 | 13
Develop Gantt Chart | On Track | 100% | 2024-10-01 | 13
Meeting with Project Supervisor | Milestone | 100% | 2024-10-07 | 1 | bar: 2024-10-07
Order bulbs | Goal | 100% | 2024-10-01 | 13 | 2024-10-01: 2; 2024-10-02: 2; 2024-10-03: 2; 2024-10-04: 2; 2024-10-05: 2; 2024-10-06: 2; 2024-10-07: 2; 2024-10-08: 2; 2024-10-09: 2; 2024-10-10: 2; 2024-10-11: 2; 2024-10-12: 2; 2024-10-13: 2
Upload Project Outline and Plan | Milestone | 100% | 2024-10-14 | 1 | bar: 2024-10-14
Holidays
Wedding | Holiday | 100% | 2024-10-09 | 8
Honeymoon | Holiday | 0% | 2025-01-10 | 31
Initial Investigation
Brainstorm additional features and functions | On Track | 0% | 2024-10-21 | 20
Create initial scripts to manipulate bulb | On Track | 0% | 2024-10-21 | 20
Explore using microphone with raspberry pi | On Track | 0% | 2024-10-21 | 20
Develop initial UI | On Track | 0% | 2024-10-21 | 20
Integration Development
Integrate microphone audio parsing with bulb control | On Track | 0% | 2024-11-10 | 20
Integrate UI with backend | On Track | 0% | 2024-11-10 | 20
Develop Authentication | On Track | 0% | 2024-11-30 | 20
Develop pairing of bulbs with application | Goal | 0% | 2024-11-30 | 20
Project Testing and Submission
Project Testing | Milestone |  | 2025-04-01 | 14
Project Report | Milestone |  | 2025-04-15 | 14
10 Minute Project Recording | Milestone |  | 2025-05-03 | 2
Project Interview | Milestone |  | 2025-05-06 | 1
Final Submission of Project | Milestone |  | 2025-05-06 | 1
To add more data, Insert new rows ABOVE this one