## Color
PROJECT: WiFi Bulb Music Sync
Ryan Urquhart |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Holiday
WiFi Bulb Music Sync
Project start date: | 2024-10-01 |  |  |  | March | [6 empty] | April | [27 empty] | May
Scrolling increment: | 181 | time axis 2025-03-31 to 2025-05-25
Milestone description | Category | Progress | Start | Days | time axis 2025-03-31 to 2025-05-25
Project Research
Develop Project Specification | On Track | 50% | 2024-10-01 | 13
Develop Gantt Chart | On Track | 50% | 2024-10-01 | 13
Meeting with Project Supervisor | Milestone | 100% | 2024-10-07 | 1
Order bulbs | Goal | 100% | 2024-10-01 | 13
Upload Project Outline and Plan | Milestone | 0% | 2024-10-14 | 1
Holidays
Wedding | Holiday | 0% | 2024-10-09 | 8
Honeymoon | Holiday | 0% | 2025-01-10 | 31
Initial Investigation
Brainstorm additional features and functions | On Track | 0% | 2024-10-21 | 20
Create initial scripts to manipulate bulb | On Track | 0% | 2024-10-21 | 20
Explore using microphone with raspberry pi | On Track | 0% | 2024-10-21 | 20
Develop initial UI | On Track | 0% | 2024-10-21 | 20
Integration Development
Integrate microphone audio parsing with bulb control | On Track | 0% | 2024-11-10 | 20
Integrate UI with backend | On Track | 0% | 2024-11-10 | 20
Develop Authentication | On Track | 0% | 2024-11-30 | 20
Develop pairing of bulbs with application | Goal | 0% | 2024-11-30 | 20
Project Testing and Submission
Project Testing | Milestone |  | 2025-04-01 | 14 | bar: 2025-04-01 to 2025-04-14
Project Report | Milestone |  | 2025-04-15 | 14 | bar: 2025-04-15 to 2025-04-28
10 Minute Project Recording | Milestone |  | 2025-05-03 | 2 | bar: 2025-05-03 to 2025-05-04
Project Interview | Milestone |  | 2025-05-06 | 1 | bar: 2025-05-06
Final Submission of Project | Milestone |  | 2025-05-06 | 1
To add more data, Insert new rows ABOVE this one